## Kaizen idea sheet
| TPM Circle No .: |  | Activity | KK | QM | PM | JH | SHE | OT | DM | E&T | KAIZEN IDEA SHEET
| TPM Circle Name.: |  | Loss no./ Step
| Dept:- |  | Result Area | P | Q | Def. A / B / C |  | C | D | S | M | Kaizen No: 8
Cell No.: 02 | Cell Name: - Sprint Line 135 |  | Machine / Stage: R-20 | [8 empty] | Operation: -Rear Assly
Kaizen Theme :-To eliminate the custmor complant of Air filter diffcult. |  |  | Idea:-Clusterwise welding of Air filter bkt
Problem / Present Status : -Air filter mounting bkt -Dim X-143 mm observed 142 to145.57 mm |  |  | Countermeasure :- Providing the clusterwise welding fixture for Air filter bkt assly after rear and Fwd joining. | [8 empty] | Bench Mark |  | 125 nos /month
[12 empty] | Target |  | Zero /month
[12 empty] | KAIZEN Start |  | 13.06.13
[12 empty] | KAIZEN Finish |  | 25.06.13
Team Members :-
[12 empty] | 1 | Neel VP
[12 empty] | 2 | Wagmare
[12 empty] | 3 | Ghayal KM
4
Benefits :-
P-
Q-
C-
D-
Indiviualy welded the Three Air filter bkt on Fwd and Rear assly then joinnary both assly |  | Before | After | Three air filter bkt joining by clusterwise welding fixture with respt pivot | [7 empty] | M-
Why-Why Analysis:- |  |  | Result:- | [8 empty] | KAIZEN SUSTAINANCE
Why 1 :-Air filter bkt X-dim 142 mm found 143 to 145.5mm | [11 empty] | What to do:- PM as per Plan
Why 2 :- Variation in rear and fwd sub assly during joining | [11 empty] | How to do:- Check the Pin,bush and block as per std on weekly basis.
Why 3 :- Indiviual bkt welded on rear and Fwd sub assly | [11 empty] | Payback period:-1 month
Why 4 :- | [11 empty] | Cost incurred for marking Kaizen
[12 empty] | Material Cost Rs. |  | Labour Cost Rs |  | Total Cost Rs
Root Cause:-Indiviual bkt welded on rear and Fwd sub assly | [11 empty] | 4k |  | 2k |  | 6k
Registration No. & Date :- 12.06.13 | [11 empty] | Scope & Plan For Horizontal Deployment
Registered By:- Neel VP | [11 empty] | Sr. | Cell | Target | Responsibility | Status
[12 empty] | 1 | Sprint line | 10.07.13 | Neel VP | Completed
Manager's Sign:- | [11 empty] | 2
3
Note on B5: MAINTENANCE: take theme as to prenevt/reduece/increase etc
Note on B6: MAINTENANCE: describe your problem in detal here
Note on B24: MAINTENANCE: start fist why with the problem
Note on B29: MAINTENANCE: find out the correct correct root cause
Note on D22: MAINTENANCE: put the self eplamatory photograps /sketch here
Note on E1: MAINTENANCE: √ tick mark the concerned pillar
Note on E3: MAINTENANCE: highlight the result
Note on E5: MAINTENANCE: idea must be opposite to the root cause
Note on E6: MAINTENANCE: elabotare the countermeasures /Kaizen done by providing/changing.
Note on E23: MAINTENANCE: result must be before & after kaizen,show up/down arrows fo betterment.this must be correlated to the theme taken.
Note on N3: MAINTENANCE: TPM COORDINATIR SHOULD GIVE THIS NO TO THE CONCERENED KZN
Note on N16: MAINTENANCE: show the increase in production/availability.reduction in cost only
Note on N25: MAINTENANCE: show with the frequency
Diam 143 Diam 143 measure 145.5 mm
measure 145.5 mm