## KAIZEN SHEET
VSME |  | Kaizen Idea Sheet | Area: | M | PU-1 | PU-2 | A | T | RM - P | RM - SM
Plant: |  | Creative Components Pvt.Ltd. | Department: | QA | Stores | Maintenance | Design | Pur | M Prod | P Prod
Kaizen Theme: |  | To reduce card breakdowns for Injection Moulding machines | Idea: | To Change SMPS into transformer which will regulate and give uniform voltage
Problem Present status :- |  |  | Part name |  |  |  | Part No:
1 | Cards used to get short more then two per month |  | Team Members | Siddlingeswar,Angadi,Vinay and Ravi hiremath
2 | Machine breakdown hrs increased. |  | Kaizen start date | 2013-05-05 |  |  | Kaizen End date | 2013-08-13
3 | Production delay due to breakdown |  | Improvement | Used Electrical Transformer Isolater instead of SMPS
Analysis: | 4W 1H Format |  | Benefits | Zero Breakdown of card from Last Three Months
What : | Card Short
Where : | Control pannel for 125 Tonnage Injection moulding machine |  | Before PPM |  |  |  | Achieved PPM
How: | Due to Solenoid wall short due to voltage fluctuations
Who : | Angadi and Vinay
When: | 2013-05-21 |  | Improvement:-Used electrical Transformer whichsupply uniform power supply even if fluctuations found in input supply.From Three month zero breakdown of cards and have saved near about 75000/-.
Root cause:- Due to volatge fluctuations the SPMS could not give uniform power supply and observed DC Cards Short more then two every month. It cost 24000/- per DC card

## Sheet1
72000